## Sheet1
2018-06-10 | Making a report about the current project demo. Making a daily plan untill 10/7
2018-06-11 | Conducting a meeting to discuss the project next deliverables and assign specific tasks.
2018-06-12 | Watching tutorials for openMV camera and getting ready to use it. Doing further enhancements on the project specifically the line detection module. Choosing the final deliverable of the project.
2018-06-13
2018-06-14
2018-06-15 | Eid Break
2018-06-16
2018-06-17
2018-06-18 | Continue enhancing the performance on the line detection module. Integrating the project on the camera/ TX2 Testing the two approaches of the object detection and compare accuracy.
2018-06-19
2018-06-20
2018-06-21
2018-06-22
2018-06-23
2018-06-24 | Finalizing the project prototpe. Enhancing performance of the algorithms. Make the testing environment of the project ready.
2018-06-25
2018-06-26
2018-06-27
2018-06-28 |  | NOTE: If OpenMv camera can't be used with YOLO object detector, we will do one of the following: 1- Choosing digital image processing approach for detecing objects with OpenMv camera instead of YOLO. 2- Using Yolo but with TX2 Nvidia board
2018-06-29
2018-06-30
10 days for documentation and presentation | Starting from 1/7 will start on the documentation of the project and the presentation. Time for printing the book is included.
2018-07-01 | Working on the content of the documentation. Continue on project testing and validation.
2018-07-02
2018-07-03
2018-07-04
2018-07-05
2018-07-06 | Integrating documentation with the other team ( Eslam Wael + Ahmed Mahmoud )
2018-07-07 | Printing the documents. Making the presentation. Doing Reharsals.
2018-07-08
2018-07-09
2018-07-10 | Project discussuion